## Dashboard
LUNAR GATEWAY SUPPLY CHAIN OPTIMIZATION FRAMEWORK
Systems Engineering & Cost Management Framework for Sustained Lunar Operations
EG7302 MEM Individual Project ¦ University of Leicester ¦ Jagathguru Pazhanaivel ¦ Student ID: 249057008
TOTAL TASKS |  | DURATION |  | COST SAVING TARGET |  | KEY DELIVERABLES
39 |  | 8 Weeks |  | 15 - 25% |  | 11
Across 4 project phases |  | 13 Feb 2026 - 10 Apr 2026 |  | USD 200M - 400M in savings |  | Reports, tools & dissertation
PROJECT PHASE SUMMARY
Phase | Title | Weeks | Start Date | End Date | Tasks | Leicester Module | Key Deliverable
Phase 1 | Systems Engineering Foundation | 1-3 | 13 Feb 2026 | 06 Mar 2026 | 12 | MN7019 | Requirements Specification + System Architecture Diagram
Phase 2 | Cost Engineering & Financial Modelling | 3-5 | 02 Mar 2026 | 20 Mar 2026 | 10 | MN7031 | Cost Model Workbook + MILP Optimization Results
Phase 3 | Lean Principles & Process Improvement | 5-6 | 16 Mar 2026 | 27 Mar 2026 | 7 | MN7032 | Value Stream Maps + FMEA Report
Phase 4 | Strategic Analysis & Dissertation | 6-8 | 23 Mar 2026 | 10 Apr 2026 | 10 | MN7036 | Dissertation + Decision Support Tool
LEARNING MILESTONES
Milestone No. | Deadline | Milestone Description | Tool / Resource | Phase
LM-01 | Week 2 | NRHO trajectory calculations demonstrated | MIT OpenCourseWare / SMAD Ch.18-19 | Phase 1
LM-02 | Week 4 | Functional cost model with validated CERs | Excel regression / Python scipy.stats | Phase 2
LM-03 | Week 5 | Working MILP model with sensitivity analysis | Python / GUROBI or PuLP | Phase 2
LM-04 | Week 6 | Value stream maps (current + future state) completed | VSM mapping software | Phase 3
LM-05 | Week 8 | Decision support tool finalized for NASA use | Excel VBA + MILP integration | Phase 4
SUBMISSION DEADLINES
No. | Submission | Type | Due Date | Notes
SD-01 | Project Proposal (EG7302) | Document | 20 Feb 2026 | Submitted — approved by supervisor
SD-02 | MN7031 Cost Engineering Submission | Coursework | 20 Mar 2026 | Cost Model Workbook + Trade Study Matrix
SD-03 | MN7032 Lean Engineering Submission | Coursework | 27 Mar 2026 | Value Stream Maps + FMEA Report
SD-04 | Final Dissertation (EG7302) | Dissertation | 10 Apr 2026 | 60 pages max, 12,000-15,000 words

## Phase 1 - Systems Eng
PHASE 1 — SYSTEMS ENGINEERING FOUNDATION (WEEKS 1-3)
Module: MN7019 Systems Engineering ¦ Establish requirements baseline, stakeholder analysis, technical budgets, and system architecture
WBS 1.0 — LITERATURE REVIEW & NRHO STUDY
WBS ID | Task Description | Week(s) | Start Date | End Date | Priority | Deliverable | Description | Type
WBS 1.1 | Review NASA Gateway Program documents and mission architecture | 1 | 13 Feb 2026 | 16 Feb 2026 | High | Annotated bibliography | Review NASA Gateway Program Office documents, published logistics studies, mission architecture reports, and technical specifications for Lunar Gateway NRHO operations. | STANDARD
WBS 1.2 | Analyse ISS logistics database (2000-2025): consumption patterns and cargo manifests | 1 | 13 Feb 2026 | 16 Feb 2026 | High | ISS logistics summary table | Analyse 25 years of ISS resupply operations data. Extract: annual consumable mass (~7,300 kg), spares (~2,500 kg), science payloads (~500 kg), resupply frequency (7-8 missions/year). | STANDARD
WBS 1.3 | Study Artemis I mission data: consumable margins and deep space supply constraints | 1 | 13 Feb 2026 | 17 Feb 2026 | High | Artemis I lessons learned log | Analyse Artemis I Mission Performance Report (2023). Key finding: Orion carried 25% margin on consumables. Document lessons for Gateway demand forecasting and safety stock modelling. | STANDARD
WBS 1.4 | Review commercial lunar lander data: IM-1 and Astrobotic Peregrine cost and reliability | 1 | 13 Feb 2026 | 17 Feb 2026 | Medium | Commercial benchmarking sheet | IM-1 (Feb 2024): 100 kg payload, $118M cost = ~$1.2M/kg — success. Astrobotic Peregrine (Jan 2024): propulsion failure. Build cost and reliability benchmarks for multi-provider strategy. | STANDARD
WBS 1.5 | Study NRHO orbital mechanics and delta-V calculations (SMAD Ch.18-19, MIT OCW) | 2 | 18 Feb 2026 | 22 Feb 2026 | High | NRHO trajectory calculation | Master NRHO dynamics: delta-V ~14 km/s vs ISS 9.5 km/s, 4-5 day transit times, monthly 2-3 day launch windows. Resources: MIT OpenCourseWare, SMAD Chapters 18-19. | LEARNING MILESTONE
WBS 1.1 — STAKEHOLDER ANALYSIS
WBS ID | Task Description | Week(s) | Start Date | End Date | Priority | Deliverable | Description | Type
WBS 1.6 | Identify all stakeholders and map interests, influence, and logistics decision authority | 2 | 18 Feb 2026 | 22 Feb 2026 | High | Stakeholder influence matrix | Map: NASA (mission authority), ESA/JAXA/CSA (international partners), SpaceX/Blue Origin/ULA (launch providers), Lockheed Martin/Northrop Grumman (spacecraft manufacturers), Crew (end users). | STANDARD
WBS 1.7 | Document multi-stakeholder coordination requirements and conflict areas | 2 | 18 Feb 2026 | 22 Feb 2026 | Medium | Stakeholder Analysis Register | Document how ESA, JAXA, and CSA partnerships affect logistics decision-making. Identify coordination requirements, conflict areas, and governance structures. | KEY DELIVERABLE
WBS 1.2 — REQUIREMENTS DEFINITION (QFD)
WBS ID | Task Description | Week(s) | Start Date | End Date | Priority | Deliverable | Description | Type
WBS 1.8 | Apply QFD to derive logistics requirements from mission objectives | 2 | 18 Feb 2026 | 24 Feb 2026 | High | QFD Matrix (House of Quality) | Apply Quality Function Deployment: translate mission objectives (crew safety, scientific output, cost efficiency) to logistics requirements via House of Quality matrix. | STANDARD
WBS 1.9 | Document launch vehicle and Gateway storage constraints | 2-3 | 20 Feb 2026 | 25 Feb 2026 | High | Vehicle and Gateway constraints register | Falcon Heavy (~$150M, 8-10k kg), Vulcan Centaur (~$200M, 7-9k kg), Starship (TBD). HALO vs I-HAB volume limits, docking port availability, crew time budgets. | STANDARD
WBS 1.10 | Write Requirements Specification Document in NASA standards format | 3 | 23 Feb 2026 | 27 Feb 2026 | High | Requirements Specification Document | Formal Requirements Specification following NASA standards: mission objectives, logistics requirements, system constraints, performance and safety requirements. | KEY DELIVERABLE
WBS 1.3 — TECHNICAL BUDGETS AND SYSTEM ARCHITECTURE
WBS ID | Task Description | Week(s) | Start Date | End Date | Priority | Deliverable | Description | Type
WBS 1.11 | Build mass budget: consumables, spares, science payloads, propellant across mission phases | 3 | 23 Feb 2026 | 01 Mar 2026 | High | Mass budget spreadsheet | O2, water, food (~7,000+ kg/yr for 4 crew), spares (~2,500 kg). Adjust for intermittent 30-90 day crew occupancy vs permanent ISS habitation. | STANDARD
WBS 1.12 | Build volume and schedule budgets: cargo mapping and critical path analysis | 3 | 25 Feb 2026 | 03 Mar 2026 | Medium | Volume + Schedule budget spreadsheets | Map cargo to HALO vs I-HAB storage. Critical path: 18-24 month lead time, monthly launch windows, 4-5 day transit, docking and unloading timeline. | STANDARD
WBS 1.13 | Develop System Architecture Diagram: full logistics flow Earth to Gateway | 3 | 02 Mar 2026 | 06 Mar 2026 | High | System Architecture Diagram | Complete Gateway logistics system diagram: Earth prep, launch, 4-5 day NRHO approach, rendezvous, docking, unloading, stowage, and disposal. | KEY DELIVERABLE

## Phase 2 - Cost Eng
PHASE 2 — COST ENGINEERING & FINANCIAL MODELLING (WEEKS 3-5)
Module: MN7031 Cost Engineering ¦ Parametric cost models, MILP optimization, trade-off analysis — target 15-25% lifecycle cost reduction ¦ Submission: 20 Mar 2026
WBS 2.0 — PARAMETRIC COST ESTIMATION
WBS ID | Task Description | Week(s) | Start Date | End Date | Priority | Deliverable | Description | Type
WBS 2.1 | Collect historical launch cost data from 50+ missions for CER regression modelling | 3 | 02 Mar 2026 | 06 Mar 2026 | High | Raw data workbook | Collect from 50+ space missions: ISS cargo (Dragon, Cygnus, Progress), commercial landers (IM-1, Peregrine), heavy-lift (Falcon Heavy, Delta IV, Atlas V). Structure into regression-ready workbook. | STANDARD
WBS 2.2 | Develop Cost Estimating Relationships (CERs): launch cost vs payload mass regressions | 3-4 | 04 Mar 2026 | 11 Mar 2026 | High | CER regression models | Build regression models: cost vs payload mass power law relationships, destination-based cost multipliers (LEO vs NRHO). Validate CERs against known mission costs. | LEARNING MILESTONE
WBS 2.3 | Define lifecycle cost categories and build parametric cost model in Excel with VBA macros | 4 | 09 Mar 2026 | 13 Mar 2026 | High | Cost Model Workbook | Lifecycle cost categories: Launch services ($150M-300M/mission), Cargo procurement ($5M-20M), Mission operations ($30M-50M/yr), Ground infrastructure ($10M-15M/yr). | KEY DELIVERABLE
WBS 2.1 — MONTE CARLO UNCERTAINTY ANALYSIS
WBS ID | Task Description | Week(s) | Start Date | End Date | Priority | Deliverable | Description | Type
WBS 2.4 | Define probability distributions and implement Monte Carlo simulation (10,000 runs) | 4 | 10 Mar 2026 | 14 Mar 2026 | High | Monte Carlo simulation + uncertainty report | Uncertain inputs: launch cost ±30%, consumption rate ±20%, mission success probability. 10,000-run simulation yields P50/P80/P90 cost estimates with confidence intervals. | STANDARD
WBS 2.2 — MILP OPTIMIZATION
WBS ID | Task Description | Week(s) | Start Date | End Date | Priority | Deliverable | Description | Type
WBS 2.5 | Formulate MILP problem: decision variables, objective function, and constraints | 4 | 11 Mar 2026 | 15 Mar 2026 | High | MILP problem formulation document | Decision variables: vehicle selection (binary), resupply frequency (integer), cargo mass per mission (continuous), safety stock per type (continuous). Objective: minimize lifecycle cost 2028-2035. | STANDARD
WBS 2.6 | Implement and solve MILP model in Python using GUROBI or PuLP solver | 5 | 16 Mar 2026 | 18 Mar 2026 | High | Working MILP model with sensitivity analysis | Implement full MILP in Python. Solve for optimal manifest plan, extract decision variable values, run sensitivity analysis. Target: 15-25% cost reduction. | MILESTONE + DELIVERABLE
WBS 2.7 | Run optimization and extract optimal manifest plan: timing, cargo, and vehicle selection | 5 | 16 Mar 2026 | 19 Mar 2026 | High | Optimization Results Report | Generate optimal 7-year manifest (2028-2035): recommended launch schedule, cargo composition, vehicle selection, safety stock levels. Document: $200M-400M savings. | KEY DELIVERABLE
WBS 2.3 — TRADE-OFF ANALYSIS
WBS ID | Task Description | Week(s) | Start Date | End Date | Priority | Deliverable | Description | Type
WBS 2.8 | Compare single-provider vs multi-provider logistics architectures | 5 | 17 Mar 2026 | 19 Mar 2026 | High | Provider architecture trade study | Compare across: Cost, Risk, Reliability, Schedule. Recommend optimal strategy for NASA Gateway program. | STANDARD
WBS 2.9 | Launch vehicle sensitivity analysis and compilation of Trade Study Matrix | 5 | 17 Mar 2026 | 20 Mar 2026 | High | Trade Study Matrix | Compare Falcon Heavy ($150M, 8-10k kg), Vulcan Centaur ($200M, 7-9k kg), Starship (TBD, 100k+ kg). Sensitivity: cost ±30%, consumption ±20%. | KEY DELIVERABLE

## Phase 3 - Lean
PHASE 3 — LEAN PRINCIPLES & PROCESS IMPROVEMENT (WEEKS 5-6)
Module: MN7032 Lean Engineering ¦ Value stream mapping, waste elimination, FMEA, reliability modelling — target 30% cycle time reduction ¦ Submission: 27 Mar 2026
WBS 3.0 — VALUE STREAM MAPPING (VSM)
WBS ID | Task Description | Week(s) | Start Date | End Date | Priority | Deliverable | Description | Type
WBS 3.1 | Document current logistics planning workflow: requirements definition to launch (18-24 month lead time) | 5 | 16 Mar 2026 | 19 Mar 2026 | High | Current state process map | Map current workflow steps: requirements definition, manifest development, approval cycles, procurement, launch readiness review, launch and delivery. Total lead time: 18-24 months. | STANDARD
WBS 3.2 | Identify and quantify waste: waiting, overproduction, and defects in logistics planning | 5-6 | 18 Mar 2026 | 22 Mar 2026 | High | Waste identification log | Lean waste categories: Waiting (approval cycles), Overproduction (excess safety margins), Defects (late payload changes), Overprocessing (redundant reviews). Quantify each in time and cost. | STANDARD
WBS 3.3 | Design future state VSM: streamlined process targeting 30% cycle time reduction | 6 | 23 Mar 2026 | 25 Mar 2026 | High | Value Stream Maps (current and future state) | Design optimised process: eliminate waste, streamline approvals, implement demand-driven safety stock models. Target: 30% planning cycle time reduction. | MILESTONE + DELIVERABLE
WBS 3.1 — FAILURE MODE AND EFFECTS ANALYSIS (FMEA)
WBS ID | Task Description | Week(s) | Start Date | End Date | Priority | Deliverable | Description | Type
WBS 3.4 | FMEA: identify failure modes in logistics chain and assess severity, occurrence, and detection | 6 | 23 Mar 2026 | 26 Mar 2026 | High | FMEA ratings table and RPN ranking | Failure modes: launch vehicle failure, propulsion anomaly, delayed launch (30-day penalty), docking failure, cargo damage. Assess: Severity × Occurrence × Detection = RPN. | STANDARD
WBS 3.5 | Develop mitigation actions for high-RPN failure modes and compile FMEA Report | 6 | 24 Mar 2026 | 27 Mar 2026 | High | FMEA Report | For top-ranked failure modes: define mitigations, assign responsibility, estimate revised RPN. Link to multi-provider strategy. Compile complete FMEA Report. | KEY DELIVERABLE
WBS 3.2 — RELIABILITY MODELLING AND QUALITY METRICS
WBS ID | Task Description | Week(s) | Start Date | End Date | Priority | Deliverable | Description | Type
WBS 3.6 | Build fault tree analysis and calculate mission success probability | 6 | 24 Mar 2026 | 26 Mar 2026 | High | Fault tree analysis report | Calculate mission success probability across logistics chain. Quality metrics: on-time delivery rate, cargo condition standard, manifest accuracy percentage. | STANDARD
WBS 3.7 | Compile process improvement recommendations with measurable targets | 6 | 25 Mar 2026 | 27 Mar 2026 | High | Process Improvement Report | Actionable recommendations with quantified targets. Integrate VSM, FMEA, and reliability findings into cohesive process improvement package. | KEY DELIVERABLE

## Phase 4 - Strategy
PHASE 4 — STRATEGIC ANALYSIS & DISSERTATION COMPLETION (WEEKS 6-8)
Module: MN7036 Strategy & International Business ¦ Strategic analysis, Decision Support Tool, dissertation writing, final submission ¦ Deadline: 10 Apr 2026
WBS 4.0 — INTERNATIONAL PARTNERSHIP STRATEGY
WBS ID | Task Description | Week(s) | Start Date | End Date | Priority | Deliverable | Description | Type
WBS 4.1 | Analyse international partnership dynamics: how ESA, JAXA, and CSA affect logistics decisions | 6-7 | 23 Mar 2026 | 30 Mar 2026 | High | Partnership dynamics analysis | Analyse ESA (I-HAB, science), JAXA (habitation components), CSA (Canadarm3 robotics). Cost-sharing, logistics authority, conflict resolution. Module: MN7036. | STANDARD
WBS 4.2 | Compare cooperative vs competitive partnership models and public-private structures | 7 | 27 Mar 2026 | 01 Apr 2026 | Medium | Partnership model comparison report | Compare: Cooperative (cost-sharing), Competitive (market procurement), Hybrid. Evaluate NASA + SpaceX/Blue Origin public-private partnership structure. | STANDARD
WBS 4.1 — TECHNOLOGY ROADMAP AND FUTURE SCENARIOS
WBS ID | Task Description | Week(s) | Start Date | End Date | Priority | Deliverable | Description | Type
WBS 4.3 | Model ISRU integration: lunar water extraction impact on consumables logistics | 7 | 28 Mar 2026 | 02 Apr 2026 | High | ISRU cost-benefit model | Lunar water ice extraction, purification, electrolysis → O2 + H2. Potential 30-40% mass reduction. Research Q4: Can ISRU reduce costs by 20%+? Break-even ~2032-2033. | STANDARD
WBS 4.4 | Model Starship impact and develop three scenario analyses (baseline, optimistic, pessimistic) | 7 | 30 Mar 2026 | 03 Apr 2026 | High | Scenario analysis report | Baseline: Falcon Heavy, no ISRU. Optimistic: Starship (80% cost reduction), ISRU (40% mass reduction). Pessimistic: costs increase, Starship delayed. Identify robust strategies. | STANDARD
WBS 4.5 | Assess Mars transferability and produce Technology Roadmap 2028-2040 | 7 | 01 Apr 2026 | 03 Apr 2026 | High | Technology Roadmap + Mars Assessment | Mars vs Gateway: 1000× farther, 6-9 month transit, 26-month windows. Identify transferable framework elements. Produce roadmap 2028-2040. | KEY DELIVERABLE
WBS 4.2 — DECISION SUPPORT TOOL
WBS ID | Task Description | Week(s) | Start Date | End Date | Priority | Deliverable | Description | Type
WBS 4.6 | Design and build Excel-based Decision Support Tool with MILP integration | 6-8 | 23 Mar 2026 | 08 Apr 2026 | High | Decision Support Tool (Excel optimizer) | Inputs: launch vehicle, frequency, cargo mass, safety stocks. Integrates Phase 2 MILP. Outputs: lifecycle cost, risk score, recommended manifest. Dashboard with sensitivity charts. | MILESTONE + DELIVERABLE
WBS 4.3 — DISSERTATION WRITING
WBS ID | Task Description | Week(s) | Start Date | End Date | Priority | Deliverable | Description | Type
WBS 4.7 | Write Dissertation Chapters 1-3: Introduction, Literature Review, and Methodology | 6-7 | 23 Mar 2026 | 01 Apr 2026 | High | Chapters 1-3 draft (4,000-5,000 words) | Ch.1 Introduction: background, problem, research questions, scope. Ch.2 Literature Review: lunar logistics, ISS ops, Artemis data, commercial landers, optimization methods. Ch.3 Methodology. | STANDARD
WBS 4.8 | Write Dissertation Chapters 4-6: Results, Discussion, and Conclusions | 7-8 | 01 Apr 2026 | 07 Apr 2026 | High | Chapters 4-6 draft (6,000-7,000 words) | Ch.4 Results: optimization, cost model, FMEA, VSM. Ch.5 Discussion: strategic analysis, partnerships, technology roadmap, limitations. Ch.6 Conclusions: findings, recommendations, future work. | STANDARD
WBS 4.9 | Compile Executive Summary (5-10 pages) for NASA stakeholders | 8 | 06 Apr 2026 | 08 Apr 2026 | High | Executive Summary for NASA | Non-technical summary: objectives, key findings, optimal resupply frequency, vehicle mix, 15-25% savings ($200M-$400M), process improvements, ISRU analysis, top 5 recommendations. | KEY DELIVERABLE
WBS 4.4 — FINALIZATION AND SUBMISSION
WBS ID | Task Description | Week(s) | Start Date | End Date | Priority | Deliverable | Description | Type
WBS 4.10 | Supervisor review, proofreading, formatting, and final dissertation submission | 8 | 07 Apr 2026 | 10 Apr 2026 | High | Final Dissertation Submission | Incorporate feedback, proofread, format per Leicester MEM standards (60-page max). Final check appendices (Cost Model, DST, VSMs, FMEA). Submit 10 April 2026. Target: 12,000-15,000 words. | KEY DELIVERABLE

## Deliverables Register
COMPLETE DELIVERABLES REGISTER
No. | Deliverable | Phase | Week | Date Due | Type | Completion Status | Supervisor Sign-off
1 | Requirements Specification Document (NASA format) | Phase 1 | Week 3 | 27 Feb 2026 | Document | Not Started
2 | System Architecture Diagram (logistics flow end-to-end) | Phase 1 | Week 3 | 06 Mar 2026 | Diagram | Not Started
3 | Technical Budget Spreadsheets (Mass / Volume / Schedule) | Phase 1 | Week 3 | 03 Mar 2026 | Spreadsheet | Not Started
4 | Cost Model Workbook (Excel with VBA macros) | Phase 2 | Week 4 | 13 Mar 2026 | Spreadsheet | Not Started
5 | Optimization Results Report (MILP — 15-25% savings target) | Phase 2 | Week 5 | 19 Mar 2026 | Report | Not Started
6 | Trade Study Matrix (vehicles and provider architectures) | Phase 2 | Week 5 | 20 Mar 2026 | Matrix | Not Started
7 | Value Stream Maps (Current State and Future State) | Phase 3 | Week 6 | 25 Mar 2026 | Diagram | Not Started
8 | FMEA Report (failure modes, RPN, mitigation plan) | Phase 3 | Week 6 | 27 Mar 2026 | Report | Not Started
9 | Decision Support Tool (Excel-based optimizer for NASA) | Phase 4 | Week 8 | 08 Apr 2026 | Tool | Not Started
10 | Executive Summary (5-10 pages for NASA stakeholders) | Phase 4 | Week 8 | 08 Apr 2026 | Document | Not Started
11 | Full Dissertation (12,000-15,000 words, 60 pages maximum) | Final | Week 8 | 10 Apr 2026 | Dissertation | Not Started

## All Tasks Tracker
ALL TASKS TRACKER — COMPLETE WBS FLAT VIEW (39 TASKS)
Jira Key | Phase | Task Description | WBS Category | Week(s) | Start Date | Due Date | Priority | Status | Type
EMP-1 | Phase 1 | Review NASA Gateway Program documents and mission architecture | WBS 1.0 — Literature Review | 1 | 13 Feb 2026 | 16 Feb 2026 | High | Not Started | STANDARD
EMP-2 | Phase 1 | Analyse ISS logistics database (2000-2025): consumption patterns and cargo manifests | WBS 1.0 — Literature Review | 1 | 13 Feb 2026 | 16 Feb 2026 | High | Not Started | STANDARD
EMP-3 | Phase 1 | Study Artemis I mission data: consumable margins and deep space supply constraints | WBS 1.0 — Literature Review | 1 | 13 Feb 2026 | 17 Feb 2026 | High | Not Started | STANDARD
EMP-4 | Phase 1 | Review commercial lunar lander data: IM-1 and Astrobotic Peregrine cost and reliability | WBS 1.0 — Literature Review | 1 | 13 Feb 2026 | 17 Feb 2026 | Medium | Not Started | STANDARD
EMP-5 | Phase 1 | Study NRHO orbital mechanics and delta-V calculations — LEARNING MILESTONE | WBS 1.0 — Literature Review | 2 | 18 Feb 2026 | 22 Feb 2026 | High | Not Started | LEARNING MILESTONE
EMP-6 | Phase 1 | Identify all stakeholders and map interests, influence, and logistics decision authority | WBS 1.1 — Stakeholder Analysis | 2 | 18 Feb 2026 | 22 Feb 2026 | High | Not Started | STANDARD
EMP-7 | Phase 1 | Document multi-stakeholder coordination requirements and conflict areas | WBS 1.1 — Stakeholder Analysis | 2 | 18 Feb 2026 | 22 Feb 2026 | Medium | Not Started | KEY DELIVERABLE
EMP-8 | Phase 1 | Apply QFD to derive logistics requirements from mission objectives | WBS 1.2 — Requirements Definition | 2 | 18 Feb 2026 | 24 Feb 2026 | High | Not Started | STANDARD
EMP-9 | Phase 1 | Document launch vehicle and Gateway storage constraints | WBS 1.2 — Requirements Definition | 2-3 | 20 Feb 2026 | 25 Feb 2026 | High | Not Started | STANDARD
EMP-10 | Phase 1 | Write Requirements Specification Document (NASA standards format) — KEY DELIVERABLE | WBS 1.2 — Requirements Definition | 3 | 23 Feb 2026 | 27 Feb 2026 | High | Not Started | KEY DELIVERABLE
EMP-11 | Phase 1 | Build mass budget: consumables, spares, science payloads, propellant | WBS 1.3 — Technical Budgets | 3 | 23 Feb 2026 | 01 Mar 2026 | High | Not Started | STANDARD
EMP-12 | Phase 1 | Build volume and schedule budgets: cargo mapping and critical path analysis | WBS 1.3 — Technical Budgets | 3 | 25 Feb 2026 | 03 Mar 2026 | Medium | Not Started | STANDARD
EMP-13 | Phase 1 | Develop System Architecture Diagram — KEY DELIVERABLE | WBS 1.3 — Technical Budgets | 3 | 02 Mar 2026 | 06 Mar 2026 | High | Not Started | KEY DELIVERABLE
EMP-14 | Phase 2 | Collect historical launch cost data from 50+ missions for CER regression | WBS 2.0 — Parametric Cost | 3 | 02 Mar 2026 | 06 Mar 2026 | High | Not Started | STANDARD
EMP-15 | Phase 2 | Develop Cost Estimating Relationships (CERs) — LEARNING MILESTONE | WBS 2.0 — Parametric Cost | 3-4 | 04 Mar 2026 | 11 Mar 2026 | High | Not Started | LEARNING MILESTONE
EMP-16 | Phase 2 | Build parametric cost model in Excel with VBA macros — KEY DELIVERABLE | WBS 2.0 — Parametric Cost | 4 | 09 Mar 2026 | 13 Mar 2026 | High | Not Started | KEY DELIVERABLE
EMP-17 | Phase 2 | Define probability distributions and implement Monte Carlo simulation (10,000 runs) | WBS 2.1 — Monte Carlo | 4 | 10 Mar 2026 | 14 Mar 2026 | High | Not Started | STANDARD
EMP-18 | Phase 2 | Formulate MILP problem: decision variables, objective function, constraints | WBS 2.2 — MILP Optimization | 4 | 11 Mar 2026 | 15 Mar 2026 | High | Not Started | STANDARD
EMP-19 | Phase 2 | Implement and solve MILP in Python using GUROBI or PuLP — MILESTONE + DELIVERABLE | WBS 2.2 — MILP Optimization | 5 | 16 Mar 2026 | 18 Mar 2026 | High | Not Started | MILESTONE + DELIVERABLE
EMP-20 | Phase 2 | Run optimization and extract optimal manifest plan — KEY DELIVERABLE | WBS 2.2 — MILP Optimization | 5 | 16 Mar 2026 | 19 Mar 2026 | High | Not Started | KEY DELIVERABLE
EMP-21 | Phase 2 | Compare single-provider vs multi-provider logistics architectures | WBS 2.3 — Trade-Off Analysis | 5 | 17 Mar 2026 | 19 Mar 2026 | High | Not Started | STANDARD
EMP-22 | Phase 2 | Launch vehicle sensitivity analysis and Trade Study Matrix — KEY DELIVERABLE | WBS 2.3 — Trade-Off Analysis | 5 | 17 Mar 2026 | 20 Mar 2026 | High | Not Started | KEY DELIVERABLE
EMP-23 | Phase 3 | Document current logistics planning workflow (18-24 month lead time) | WBS 3.0 — Value Stream Mapping | 5 | 16 Mar 2026 | 19 Mar 2026 | High | Not Started | STANDARD
EMP-24 | Phase 3 | Identify and quantify waste: waiting, overproduction, defects | WBS 3.0 — Value Stream Mapping | 5-6 | 18 Mar 2026 | 22 Mar 2026 | High | Not Started | STANDARD
EMP-25 | Phase 3 | Design future state VSM targeting 30% cycle time reduction — MILESTONE + DELIVERABLE | WBS 3.0 — Value Stream Mapping | 6 | 23 Mar 2026 | 25 Mar 2026 | High | Not Started | MILESTONE + DELIVERABLE
EMP-26 | Phase 3 | FMEA: identify failure modes and assess severity, occurrence, detection | WBS 3.1 — FMEA | 6 | 23 Mar 2026 | 26 Mar 2026 | High | Not Started | STANDARD
EMP-27 | Phase 3 | Develop mitigation actions for high-RPN failure modes — KEY DELIVERABLE | WBS 3.1 — FMEA | 6 | 24 Mar 2026 | 27 Mar 2026 | High | Not Started | KEY DELIVERABLE
EMP-28 | Phase 3 | Build fault tree analysis and calculate mission success probability | WBS 3.2 — Reliability | 6 | 24 Mar 2026 | 26 Mar 2026 | High | Not Started | STANDARD
EMP-29 | Phase 3 | Compile process improvement report with measurable targets — KEY DELIVERABLE | WBS 3.2 — Reliability | 6 | 25 Mar 2026 | 27 Mar 2026 | High | Not Started | KEY DELIVERABLE
EMP-30 | Phase 4 | Analyse international partnership dynamics: ESA, JAXA, and CSA | WBS 4.0 — Partnership Strategy | 6-7 | 23 Mar 2026 | 30 Mar 2026 | High | Not Started | STANDARD
EMP-31 | Phase 4 | Compare cooperative vs competitive partnership models | WBS 4.0 — Partnership Strategy | 7 | 27 Mar 2026 | 01 Apr 2026 | Medium | Not Started | STANDARD
EMP-32 | Phase 4 | Model ISRU integration: lunar water extraction impact on logistics | WBS 4.1 — Technology Roadmap | 7 | 28 Mar 2026 | 02 Apr 2026 | High | Not Started | STANDARD
EMP-33 | Phase 4 | Model Starship impact and develop three scenario analyses | WBS 4.1 — Technology Roadmap | 7 | 30 Mar 2026 | 03 Apr 2026 | High | Not Started | STANDARD
EMP-34 | Phase 4 | Assess Mars transferability and produce Technology Roadmap 2028-2040 — KEY DELIVERABLE | WBS 4.1 — Technology Roadmap | 7 | 01 Apr 2026 | 03 Apr 2026 | High | Not Started | KEY DELIVERABLE
EMP-35 | Phase 4 | Design and build Excel Decision Support Tool with MILP integration — MILESTONE + DELIVERABLE | WBS 4.2 — Decision Support Tool | 6-8 | 23 Mar 2026 | 08 Apr 2026 | High | Not Started | MILESTONE + DELIVERABLE
EMP-36 | Phase 4 | Write Dissertation Chapters 1-3: Introduction, Literature Review, Methodology | WBS 4.3 — Dissertation Writing | 6-7 | 23 Mar 2026 | 01 Apr 2026 | High | Not Started | STANDARD
EMP-37 | Phase 4 | Write Dissertation Chapters 4-6: Results, Discussion, Conclusions | WBS 4.3 — Dissertation Writing | 7-8 | 01 Apr 2026 | 07 Apr 2026 | High | Not Started | STANDARD
EMP-38 | Phase 4 | Compile Executive Summary (5-10 pages) for NASA stakeholders — KEY DELIVERABLE | WBS 4.3 — Dissertation Writing | 8 | 06 Apr 2026 | 08 Apr 2026 | High | Not Started | KEY DELIVERABLE
EMP-39 | Phase 4 | Supervisor review, proofreading, formatting, and final dissertation submission | WBS 4.4 — Finalization | 8 | 07 Apr 2026 | 10 Apr 2026 | High | Not Started | KEY DELIVERABLE
LEGEND: KEY DELIVERABLE — highlighted amber background in Type column ¦ LEARNING MILESTONE — highlighted steel blue in Type column ¦ MILESTONE + DELIVERABLE — both criteria apply