## Dashboard
LUNAR GATEWAY SUPPLY CHAIN OPTIMIZATION FRAMEWORK
Systems Engineering & Cost Management Framework for Sustained Lunar Operations
EG7302 MEM Individual Project ¦ University of Leicester ¦ Jagathguru Pazhanaivel ¦ Student ID: 249057008
TOTAL TASKS |  | DURATION |  | COST SAVING TARGET |  | KEY DELIVERABLES
39 |  | 26 Weeks |  | 15 - 25% |  | 11
Across 4 project phases |  | 18 Feb 2026 - 18 Aug 2026 |  | USD 200M - 400M in savings |  | Reports, tools & dissertation
PROJECT PHASE SUMMARY
Phase | Title | Weeks | Start Date | End Date | Tasks | Leicester Module | Key Deliverable
Phase 1 | Systems Engineering Foundation | 1-6 | 18 Feb 2026 | 29 Mar 2026 | 14 | MN7019 | Requirements Specification + System Architecture Diagram
Phase 2 | Cost Engineering & Financial Modelling | 7-12 | 01 Apr 2026 | 10 May 2026 | 9 | MN7031 | Cost Model Workbook + MILP Optimization Results
Phase 3 | Lean Principles & Process Improvement | 13-16 | 13 May 2026 | 07 Jun 2026 | 6 | MN7032 | Value Stream Maps + FMEA Report
Phase 4 | Strategic Analysis & Dissertation | 17-26 | 10 Jun 2026 | 16 Aug 2026 | 10 | MN7036 | Dissertation + Decision Support Tool
LEARNING MILESTONES
Milestone No. | Deadline | Milestone Description | Tool / Resource | Phase
LM-01 | Week 2 | NRHO trajectory calculations demonstrated | MIT OpenCourseWare / SMAD Ch.18-19 | Phase 1
LM-02 | Week 5 | Functional cost model with validated CERs | Excel regression / Python scipy.stats | Phase 2
LM-03 | Week 6 | Working MILP model with sensitivity analysis | Python / GUROBI or PuLP | Phase 2
LM-04 | Week 8 | Value stream maps (current + future state) completed | VSM mapping software | Phase 3
LM-05 | Week 10 | Decision support tool finalized for NASA use | Excel VBA + MILP integration | Phase 4

## Phase 1 - Systems Eng
PHASE 1 — SYSTEMS ENGINEERING FOUNDATION (WEEKS 1-6)
Module: MN7019 Systems Engineering ¦ Establish requirements baseline, stakeholder analysis, technical budgets, and system architecture
WBS 1.0 — LITERATURE REVIEW
WBS ID | Task Description | Week(s) | Start Date | End Date | Priority | Deliverable | Description | Type
WBS 1.1 | Review NASA Gateway Program documents and mission architecture | 1 | 18 Feb 2026 | 22 Feb 2026 | High | Annotated bibliography | Review NASA Gateway Program Office documents, published logistics studies, mission architecture reports, and technical specifications for Lunar Gateway NRHO operations. | STANDARD
WBS 1.2 | Analyse ISS logistics database (2000-2025): consumption patterns and cargo manifests | 1 | 18 Feb 2026 | 22 Feb 2026 | High | ISS logistics summary table | Analyse 25 years of ISS resupply operations data. Extract: annual consumable mass (~7,300 kg), spares (~2,500 kg), science payloads (~500 kg), resupply frequency (7-8 missions/year). | STANDARD
WBS 1.3 | Study Artemis I mission data: consumable margins and deep space supply constraints | 2 | 25 Feb 2026 | 01 Mar 2026 | High | Artemis I lessons learned log | Analyse Artemis I Mission Performance Report (2023). Key finding: Orion carried 25% margin on consumables. Document lessons for Gateway demand forecasting and safety stock modelling. | STANDARD
WBS 1.4 | Review commercial lunar lander data: IM-1 and Astrobotic Peregrine cost and reliability | 2 | 25 Feb 2026 | 01 Mar 2026 | Medium | Commercial benchmarking sheet | IM-1 (Feb 2024): 100 kg payload, $118M cost = ~$1.2M/kg — success. Astrobotic Peregrine (Jan 2024): propulsion failure. Build cost and reliability benchmarks for multi-provider strategy. | STANDARD
WBS 1.5 | Study NRHO orbital mechanics and delta-V calculations (SMAD Ch.18-19, MIT OCW) | 2 | 25 Feb 2026 | 01 Mar 2026 | High | NRHO trajectory calculation | Master NRHO dynamics: delta-V ~14 km/s vs ISS 9.5 km/s, 4-5 day transit times, monthly 2-3 day launch windows. Resources: MIT OpenCourseWare Aerospace Engineering, SMAD Chapters 18-19. | LEARNING MILESTONE
WBS 1.1 — STAKEHOLDER ANALYSIS
WBS ID | Task Description | Week(s) | Start Date | End Date | Priority | Deliverable | Description | Type
WBS 1.6 | Identify all stakeholders and map interests, influence, and logistics decision authority | 2-3 | 25 Feb 2026 | 08 Mar 2026 | High | Stakeholder influence matrix | Map: NASA (mission authority, safety), ESA / JAXA / CSA (international partners, cost sharing), SpaceX / Blue Origin / ULA (launch providers), Lockheed Martin / Northrop Grumman (spacecraft manufacturers), Crew (end users). | STANDARD
WBS 1.7 | Document multi-stakeholder coordination requirements and conflict areas | 3 | 04 Mar 2026 | 08 Mar 2026 | Medium | Stakeholder Analysis Register | Document how ESA, JAXA, and CSA partnerships affect logistics decision-making. Identify coordination requirements, conflict areas, and governance structures for multi-stakeholder logistics planning. | KEY DELIVERABLE
WBS 1.2 — REQUIREMENTS DEFINITION (QFD)
WBS ID | Task Description | Week(s) | Start Date | End Date | Priority | Deliverable | Description | Type
WBS 1.8 | Apply QFD to derive logistics requirements from mission objectives | 3-4 | 04 Mar 2026 | 15 Mar 2026 | High | QFD Matrix (House of Quality) | Apply Quality Function Deployment methodology: translate mission objectives (crew safety, scientific output, cost efficiency) to logistics requirements via House of Quality matrix. Prioritise by importance and technical difficulty. | STANDARD
WBS 1.9 | Document launch vehicle and Gateway storage constraints | 4 | 11 Mar 2026 | 15 Mar 2026 | High | Vehicle and Gateway constraints register | Falcon Heavy (~$150M, 8-10k kg), Vulcan Centaur (~$200M, 7-9k kg), Starship (TBD). HALO vs I-HAB volume limits, docking port availability, crew time budgets for unloading operations. | STANDARD
WBS 1.10 | Write Requirements Specification Document in NASA standards format | 5 | 18 Mar 2026 | 22 Mar 2026 | High | Requirements Specification Document | Formal Requirements Specification following NASA standards: mission objectives, logistics requirements, system constraints, performance requirements, safety requirements. References QFD outputs. | KEY DELIVERABLE
WBS 1.3 — TECHNICAL BUDGETS AND SYSTEM ARCHITECTURE
WBS ID | Task Description | Week(s) | Start Date | End Date | Priority | Deliverable | Description | Type
WBS 1.11 | Build mass budget: consumables, spares, science payloads, propellant across mission phases | 4-5 | 11 Mar 2026 | 22 Mar 2026 | High | Mass budget spreadsheet | O2, water, food (~7,000+ kg/yr for 4 crew), spares (~2,500 kg). Adjust for intermittent 30-90 day crew occupancy vs permanent ISS habitation. | STANDARD
WBS 1.12 | Build volume budget: cargo mapped to HALO vs I-HAB, pressurised and unpressurised carriers | 5 | 18 Mar 2026 | 22 Mar 2026 | Medium | Volume budget spreadsheet | Map cargo categories to Gateway storage: HALO (Habitation and Logistics Outpost, pressurised), I-HAB (ESA/JAXA International Habitation Module), unpressurised logistics carriers. Document volume constraints per module. | STANDARD
WBS 1.13 | Build schedule budget: critical path from launch readiness to cargo delivery | 5 | 18 Mar 2026 | 22 Mar 2026 | Medium | Schedule budget Gantt chart | Critical path analysis: 18-24 month launch preparation lead time, monthly 2-3 day launch windows, 4-5 day Earth-to-Gateway transit, docking and unloading operations timeline. | STANDARD
WBS 1.14 | Develop System Architecture Diagram: full logistics flow Earth to Launch to Transit to Dock to Unload | 6 | 25 Mar 2026 | 29 Mar 2026 | High | System Architecture Diagram | Complete Gateway logistics system diagram: Earth cargo prep, launch facility, Falcon Heavy / Vulcan Centaur / Starship ascent, 4-5 day NRHO approach, Gateway rendezvous, docking, unloading, stowage, and disposal. | KEY DELIVERABLE

## Phase 2 - Cost Eng
PHASE 2 — COST ENGINEERING & FINANCIAL MODELLING (WEEKS 7-12)
Module: MN7031 Cost Engineering ¦ Parametric cost models, MILP optimization, trade-off analysis — target 15-25% lifecycle cost reduction
WBS 2.0 — PARAMETRIC COST ESTIMATION
WBS ID | Task Description | Week(s) | Start Date | End Date | Priority | Deliverable | Description | Type
WBS 2.1 | Collect historical launch cost data from 50+ missions for CER regression modelling | 7 | 01 Apr 2026 | 05 Apr 2026 | High | Raw data workbook | Collect from 50+ space missions: ISS cargo (Dragon, Cygnus, Progress costs and payload masses), commercial landers (IM-1, Peregrine), heavy-lift (Falcon Heavy, Delta IV, Atlas V). Structure into regression-ready workbook. | STANDARD
WBS 2.2 | Develop Cost Estimating Relationships (CERs): launch cost vs payload mass regressions | 7-8 | 01 Apr 2026 | 12 Apr 2026 | High | CER regression models | Build regression models: cost vs payload mass power law relationships, destination-based cost multipliers (LEO vs NRHO). Validate CERs against known mission costs. Tools: Excel regression, Python scipy.stats. | LEARNING MILESTONE
WBS 2.3 | Define lifecycle cost categories and build parametric cost model in Excel with VBA macros | 8-9 | 08 Apr 2026 | 19 Apr 2026 | High | Cost Model Workbook | Lifecycle cost categories: Launch services ($150M-300M/mission), Cargo procurement ($5M-20M), Mission operations ($30M-50M/yr), Ground infrastructure ($10M-15M/yr). Build Excel model with automated VBA calculations. | KEY DELIVERABLE
WBS 2.1 — MONTE CARLO UNCERTAINTY ANALYSIS
WBS ID | Task Description | Week(s) | Start Date | End Date | Priority | Deliverable | Description | Type
WBS 2.4 | Define probability distributions and implement Monte Carlo simulation (10,000 runs) | 9-10 | 15 Apr 2026 | 26 Apr 2026 | High | Monte Carlo simulation script + uncertainty report | Uncertain inputs: launch cost +-30%, consumption rate +-20%, mission success probability from historical data. 10,000-run simulation yields P50/P80/P90 cost estimates with confidence intervals. Tools: Python Scipy/Numpy. | STANDARD
WBS 2.2 — MILP OPTIMIZATION
WBS ID | Task Description | Week(s) | Start Date | End Date | Priority | Deliverable | Description | Type
WBS 2.5 | Formulate MILP problem: decision variables, objective function, and constraints | 9-10 | 15 Apr 2026 | 26 Apr 2026 | High | MILP problem formulation document | Decision variables: vehicle selection (binary), resupply frequency (integer), cargo mass per mission (continuous), safety stock per consumable type (continuous). Objective: minimize total lifecycle cost 2028-2035. Constraints: consumption, storage, launch windows, safety stocks, payload capacity. | STANDARD
WBS 2.6 | Implement and solve MILP model in Python using GUROBI or PuLP solver | 10 | 22 Apr 2026 | 26 Apr 2026 | High | Working MILP model with sensitivity analysis | Implement full MILP in Python using GUROBI or PuLP library. Solve for optimal manifest plan, extract decision variable values, run sensitivity analysis, validate against baseline scenarios. Target: 15-25% cost reduction. | MILESTONE + DELIVERABLE
WBS 2.7 | Run optimization and extract optimal manifest plan: timing, cargo, and vehicle selection | 10-11 | 22 Apr 2026 | 03 May 2026 | High | Optimization Results Report | Generate optimal 7-year manifest (2028-2035): recommended launch schedule, cargo composition per mission, vehicle selection, safety stock levels. Document: 15-25% cost savings = $200M-400M over 7 years. | KEY DELIVERABLE
WBS 2.3 — TRADE-OFF ANALYSIS
WBS ID | Task Description | Week(s) | Start Date | End Date | Priority | Deliverable | Description | Type
WBS 2.8 | Compare single-provider vs multi-provider logistics architectures | 11 | 29 Apr 2026 | 03 May 2026 | High | Provider architecture trade study | Compare across: Cost (single-source vs multi-source pricing), Risk (concentration vs redundancy), Reliability (single failure mode vs diversification), Schedule (simple vs complex coordination). Recommend optimal strategy. | STANDARD
WBS 2.9 | Launch vehicle sensitivity analysis and compilation of Trade Study Matrix | 11-12 | 29 Apr 2026 | 10 May 2026 | High | Trade Study Matrix | Compare Falcon Heavy ($150M/launch, 8-10k kg, operational), Vulcan Centaur ($200M/launch, 7-9k kg, new 2024), Starship (TBD cost, 100k+ kg, high risk). Sensitivity: launch cost +-30%, consumption +-20%. Compile comprehensive Trade Study Matrix. | KEY DELIVERABLE

## Phase 3 - Lean
PHASE 3 — LEAN PRINCIPLES & PROCESS IMPROVEMENT (WEEKS 13-16)
Module: MN7032 Lean Engineering ¦ Value stream mapping, waste elimination, FMEA, and reliability modelling — target 30% cycle time reduction
WBS 3.0 — VALUE STREAM MAPPING (VSM)
WBS ID | Task Description | Week(s) | Start Date | End Date | Priority | Deliverable | Description | Type
WBS 3.1 | Document current logistics planning workflow: requirements definition to launch (18-24 month lead time) | 13 | 13 May 2026 | 17 May 2026 | High | Current state process map | Map current workflow steps: requirements definition, cargo manifest development, internal reviews and approval cycles, procurement and cargo preparation, launch readiness review, launch and delivery. Document total lead time: 18-24 months. | STANDARD
WBS 3.2 | Identify and quantify waste: waiting, overproduction, and defects in logistics planning | 13 | 13 May 2026 | 17 May 2026 | High | Waste identification log | Lean waste categories: Waiting (long approval cycles for cargo manifests), Overproduction (excess safety margins from poor demand models), Defects (late-stage payload changes causing schedule slips), Overprocessing (redundant reviews across international partners). Quantify each waste in time and cost. | STANDARD
WBS 3.3 | Design future state VSM: streamlined process targeting 30% cycle time reduction | 14 | 20 May 2026 | 24 May 2026 | High | Value Stream Maps (current and future state) | Design optimised logistics planning process: eliminate identified waste, streamline approval workflows, implement demand-driven safety stock models. Target: 30% reduction in planning cycle time. Create future state VSM with improvement metrics. | MILESTONE + DELIVERABLE
WBS 3.1 — FAILURE MODE AND EFFECTS ANALYSIS (FMEA)
WBS ID | Task Description | Week(s) | Start Date | End Date | Priority | Deliverable | Description | Type
WBS 3.4 | FMEA: identify failure modes in logistics chain and assess severity, occurrence, and detection | 14-15 | 20 May 2026 | 31 May 2026 | High | FMEA ratings table and RPN ranking | Failure modes: launch vehicle failure (cargo loss), spacecraft propulsion anomaly (Peregrine-type), delayed launch (missed window - 30-day penalty), Gateway docking failure, cargo contamination or damage in transit. Assess each: Severity x Occurrence x Detection = Risk Priority Number (RPN). | STANDARD
WBS 3.5 | Develop mitigation actions for high-RPN failure modes and compile FMEA Report | 15 | 27 May 2026 | 31 May 2026 | High | FMEA Report | For top-ranked failure modes: define specific mitigation actions, assign responsibility (NASA, commercial partner), estimate revised RPN post-mitigation, link to multi-provider strategy recommendations. Compile complete FMEA Report. | KEY DELIVERABLE
WBS 3.2 — RELIABILITY MODELLING AND QUALITY METRICS
WBS ID | Task Description | Week(s) | Start Date | End Date | Priority | Deliverable | Description | Type
WBS 3.6 | Build fault tree analysis and compile process improvement recommendations | 15-16 | 27 May 2026 | 07 Jun 2026 | High | Process Improvement Report | Fault tree analysis: calculate mission success probability across the logistics chain. Quality metrics: on-time delivery rate target, cargo condition upon receipt standard, manifest accuracy percentage. Compile actionable process improvement recommendations with measurable targets. | KEY DELIVERABLE

## Phase 4 - Strategy
PHASE 4 — STRATEGIC ANALYSIS & DISSERTATION COMPLETION (WEEKS 17-26)
Module: MN7036 Strategy & International Business ¦ Strategic analysis, Decision Support Tool, full dissertation writing, Executive Summary, final submission
WBS 4.0 — INTERNATIONAL PARTNERSHIP STRATEGY
WBS ID | Task Description | Week(s) | Start Date | End Date | Priority | Deliverable | Description | Type
WBS 4.1 | Analyse international partnership dynamics: how ESA, JAXA, and CSA affect logistics decisions | 17 | 10 Jun 2026 | 14 Jun 2026 | High | Partnership dynamics analysis | Analyse how partnerships shape Gateway logistics: ESA (I-HAB module, science contributions), JAXA (habitation module components), CSA (Canadarm3 robotics for logistics operations). Key questions: cost-sharing agreements, logistics authority, conflict resolution mechanisms. Module: MN7036. | STANDARD
WBS 4.2 | Compare cooperative vs competitive partnership models and evaluate public-private partnership structures | 17-18 | 10 Jun 2026 | 21 Jun 2026 | Medium | Partnership model comparison report | Compare models: Cooperative (cost-sharing agreements, capability contributions), Competitive (market-based procurement), Hybrid (international partners for modules, commercial for logistics). Evaluate NASA + SpaceX / Blue Origin public-private partnership structure. | STANDARD
WBS 4.1 — TECHNOLOGY ROADMAP AND FUTURE SCENARIOS
WBS ID | Task Description | Week(s) | Start Date | End Date | Priority | Deliverable | Description | Type
WBS 4.3 | Model ISRU integration: lunar water extraction impact on consumables logistics | 18-19 | 17 Jun 2026 | 28 Jun 2026 | High | ISRU cost-benefit model | Lunar water ice in permanently shadowed polar craters. Extraction to purification to electrolysis yields O2 + H2. Potential 30-40% consumables mass reduction. Research Question 4: Can ISRU reduce logistics costs by 20%+? Model break-even: approximately 2032-2033. | STANDARD
WBS 4.4 | Model Starship impact and develop three scenario analyses (baseline, optimistic, pessimistic) | 19 | 24 Jun 2026 | 28 Jun 2026 | High | Scenario analysis report | Scenario 1 Baseline: Falcon Heavy, no ISRU, conventional vehicles. Scenario 2 Optimistic: Starship operational (80% cost reduction), ISRU providing 40% mass reduction. Scenario 3 Pessimistic: launch costs increase, Starship delayed, higher consumption than predicted. Identify strategies robust across all three. | STANDARD
WBS 4.5 | Assess Mars transferability and produce Technology Roadmap 2028-2040 | 20 | 01 Jul 2026 | 05 Jul 2026 | High | Technology Roadmap 2028-2040 and Mars Assessment | Mars scaling vs Gateway: 1000x farther, 6-9 month transit, 26-month launch windows, no recovery option. Identify framework elements transferable to Mars logistics. Produce technology roadmap 2028-2040. | KEY DELIVERABLE
WBS 4.2 — DECISION SUPPORT TOOL
WBS ID | Task Description | Week(s) | Start Date | End Date | Priority | Deliverable | Description | Type
WBS 4.6 | Design and build Excel-based Decision Support Tool with MILP integration | 17-21 | 10 Jun 2026 | 12 Jul 2026 | High | Decision Support Tool (Excel optimizer) | Inputs: launch vehicle, resupply frequency, cargo mass targets, safety stock levels. Optimizer integrates Phase 2 MILP results. Outputs: lifecycle cost estimate, risk score, recommended manifest. Dashboard: sensitivity charts, scenario comparison. Target users: NASA Gateway program office managers. | MILESTONE + DELIVERABLE
WBS 4.3 — DISSERTATION WRITING
WBS ID | Task Description | Week(s) | Start Date | End Date | Priority | Deliverable | Description | Type
WBS 4.7 | Write Dissertation Chapters 1-3: Introduction, Literature Review, and Methodology | 17-20 | 10 Jun 2026 | 05 Jul 2026 | High | Chapters 1-3 draft (4,000-5,000 words) | Chapter 1 Introduction: background, problem statement, research questions, project scope. Chapter 2 Literature Review: lunar logistics, ISS operations, Artemis data, commercial landers, optimization methods. Chapter 3 Methodology: systems engineering framework, cost engineering methods, lean approach, strategic analysis. | STANDARD
WBS 4.8 | Write Dissertation Chapters 4-6: Results, Discussion, and Conclusions | 20-22 | 01 Jul 2026 | 19 Jul 2026 | High | Chapters 4-6 draft (6,000-7,000 words) | Chapter 4 Results: optimization outputs, cost model results, FMEA findings, VSM improvements. Chapter 5 Discussion: strategic analysis, partnership implications, technology roadmap, limitations. Chapter 6 Conclusions: key findings, recommendations, future work including Mars transferability. | STANDARD
WBS 4.9 | Compile Executive Summary (5-10 pages) for NASA stakeholders | 22 | 15 Jul 2026 | 19 Jul 2026 | High | Executive Summary for NASA | Non-technical 5-10 page summary: project overview and objectives, key findings including optimal resupply frequency and vehicle mix, cost savings 15-25% ($200M-$400M over 7 years), process improvements 30% cycle time reduction, ISRU break-even analysis, top 5 recommendations for NASA Gateway program office. | KEY DELIVERABLE
WBS 4.4 — FINALIZATION AND SUBMISSION
WBS ID | Task Description | Week(s) | Start Date | End Date | Priority | Deliverable | Description | Type
WBS 4.10 | Supervisor review, proofreading, formatting, and final dissertation submission | 23-26 | 22 Jul 2026 | 16 Aug 2026 | High | Final Dissertation Submission | Week 23: incorporate supervisor feedback on full draft. Week 24: proofread and format per University of Leicester MEM standards, verify 60-page maximum. Week 25: final check of all appendices (Cost Model Workbook, Decision Support Tool, VSMs, FMEA Report). Week 26: submit final dissertation. Target: 12,000-15,000 words. | KEY DELIVERABLE

## Deliverables Register
COMPLETE DELIVERABLES REGISTER
Lunar Gateway Supply Chain Optimization Framework ¦ EG7302 MEM Individual Project ¦ University of Leicester
No. | Deliverable | Phase | Week | Date Due | Leicester Module | Type | Completion Status | Supervisor Sign-off
1 | Requirements Specification Document (NASA format) | Phase 1 | Week 5 | 22 Mar 2026 | MN7019 | Document | Not Started
2 | System Architecture Diagram (logistics flow end-to-end) | Phase 1 | Week 6 | 29 Mar 2026 | MN7019 | Diagram | Not Started
3 | Technical Budget Spreadsheets (Mass / Volume / Schedule) | Phase 1 | Week 6 | 29 Mar 2026 | MN7019 | Spreadsheet | Not Started
4 | Cost Model Workbook (Excel with VBA macros) | Phase 2 | Week 9 | 19 Apr 2026 | MN7031 | Spreadsheet | Not Started
5 | Optimization Results Report (MILP - 15-25% savings target) | Phase 2 | Week 11 | 03 May 2026 | MN7031 | Report | Not Started
6 | Trade Study Matrix (vehicles and provider architectures) | Phase 2 | Week 12 | 10 May 2026 | MN7031 | Matrix | Not Started
7 | Value Stream Maps (Current State and Future State) | Phase 3 | Week 14 | 24 May 2026 | MN7032 | Diagram | Not Started
8 | FMEA Report (failure modes, RPN, mitigation plan) | Phase 3 | Week 15 | 31 May 2026 | MN7032 | Report | Not Started
9 | Decision Support Tool (Excel-based optimizer for NASA) | Phase 4 | Week 21 | 12 Jul 2026 | MN7036 | Tool | Not Started
10 | Executive Summary (5-10 pages for NASA stakeholders) | Phase 4 | Week 22 | 19 Jul 2026 | MN7036 | Document | Not Started
11 | Full Dissertation (12,000-15,000 words, 60 pages maximum) | Final | Week 26 | 16 Aug 2026 | All Modules | Dissertation | Not Started

## All Tasks Tracker
ALL TASKS TRACKER — COMPLETE WBS FLAT VIEW (39 TASKS)
Jira Key | Phase | Task Description | WBS Category | Week(s) | Start Date | Due Date | Priority | Status | Type
KAN-1 | Phase 1 | Review NASA Gateway Program documents and mission architecture | WBS 1.0 — Literature Review | 1 | 18 Feb 2026 | 22 Feb 2026 | High | Not Started | STANDARD
KAN-2 | Phase 1 | Analyse ISS logistics database (2000-2025): consumption patterns and cargo manifests | WBS 1.0 — Literature Review | 1 | 18 Feb 2026 | 22 Feb 2026 | High | Not Started | STANDARD
KAN-3 | Phase 1 | Study Artemis I mission data: consumable margins and deep space supply constraints | WBS 1.0 — Literature Review | 2 | 25 Feb 2026 | 01 Mar 2026 | High | Not Started | STANDARD
KAN-4 | Phase 1 | Review commercial lunar lander data: IM-1 and Astrobotic Peregrine cost and reliability | WBS 1.0 — Literature Review | 2 | 25 Feb 2026 | 01 Mar 2026 | Medium | Not Started | STANDARD
KAN-5 | Phase 1 | Study NRHO orbital mechanics and delta-V calculations — LEARNING MILESTONE | WBS 1.0 — Literature Review | 2 | 25 Feb 2026 | 01 Mar 2026 | High | Not Started | LEARNING MILESTONE
KAN-6 | Phase 1 | Identify all stakeholders and map interests, influence, and logistics decision authority | WBS 1.1 — Stakeholder Analysis | 2-3 | 25 Feb 2026 | 08 Mar 2026 | High | Not Started | STANDARD
KAN-7 | Phase 1 | Document multi-stakeholder coordination requirements and conflict areas | WBS 1.1 — Stakeholder Analysis | 3 | 04 Mar 2026 | 08 Mar 2026 | Medium | Not Started | KEY DELIVERABLE
KAN-8 | Phase 1 | Apply QFD to derive logistics requirements from mission objectives | WBS 1.2 — Requirements Definition | 3-4 | 04 Mar 2026 | 15 Mar 2026 | High | Not Started | STANDARD
KAN-9 | Phase 1 | Document launch vehicle and Gateway storage constraints | WBS 1.2 — Requirements Definition | 4 | 11 Mar 2026 | 15 Mar 2026 | High | Not Started | STANDARD
KAN-10 | Phase 1 | Write Requirements Specification Document (NASA standards format) — KEY DELIVERABLE | WBS 1.2 — Requirements Definition | 5 | 18 Mar 2026 | 22 Mar 2026 | High | Not Started | KEY DELIVERABLE
KAN-11 | Phase 1 | Build mass budget: consumables, spares, science payloads, propellant | WBS 1.3 — Technical Budgets | 4-5 | 11 Mar 2026 | 22 Mar 2026 | High | Not Started | STANDARD
KAN-12 | Phase 1 | Build volume budget: cargo mapped to HALO vs I-HAB | WBS 1.3 — Technical Budgets | 5 | 18 Mar 2026 | 22 Mar 2026 | Medium | Not Started | STANDARD
KAN-13 | Phase 1 | Build schedule budget: critical path from launch readiness to cargo delivery | WBS 1.3 — Technical Budgets | 5 | 18 Mar 2026 | 22 Mar 2026 | Medium | Not Started | STANDARD
KAN-14 | Phase 1 | Develop System Architecture Diagram — KEY DELIVERABLE | WBS 1.3 — Technical Budgets | 6 | 25 Mar 2026 | 29 Mar 2026 | High | Not Started | KEY DELIVERABLE
KAN-15 | Phase 2 | Collect historical launch cost data from 50+ missions for CER regression | WBS 2.0 — Parametric Cost | 7 | 01 Apr 2026 | 05 Apr 2026 | High | Not Started | STANDARD
KAN-16 | Phase 2 | Develop Cost Estimating Relationships (CERs) — LEARNING MILESTONE | WBS 2.0 — Parametric Cost | 7-8 | 01 Apr 2026 | 12 Apr 2026 | High | Not Started | LEARNING MILESTONE
KAN-17 | Phase 2 | Build parametric cost model in Excel with VBA macros — KEY DELIVERABLE | WBS 2.0 — Parametric Cost | 8-9 | 08 Apr 2026 | 19 Apr 2026 | High | Not Started | KEY DELIVERABLE
KAN-18 | Phase 2 | Define probability distributions and implement Monte Carlo simulation (10,000 runs) | WBS 2.1 — Monte Carlo | 9-10 | 15 Apr 2026 | 26 Apr 2026 | High | Not Started | STANDARD
KAN-19 | Phase 2 | Formulate MILP problem: decision variables, objective function, constraints | WBS 2.2 — MILP Optimization | 9-10 | 15 Apr 2026 | 26 Apr 2026 | High | Not Started | STANDARD
KAN-20 | Phase 2 | Implement and solve MILP in Python using GUROBI or PuLP — MILESTONE + DELIVERABLE | WBS 2.2 — MILP Optimization | 10 | 22 Apr 2026 | 26 Apr 2026 | High | Not Started | MILESTONE + DELIVERABLE
KAN-21 | Phase 2 | Run optimization and extract optimal manifest plan — KEY DELIVERABLE | WBS 2.2 — MILP Optimization | 10-11 | 22 Apr 2026 | 03 May 2026 | High | Not Started | KEY DELIVERABLE
KAN-22 | Phase 2 | Compare single-provider vs multi-provider logistics architectures | WBS 2.3 — Trade-Off Analysis | 11 | 29 Apr 2026 | 03 May 2026 | High | Not Started | STANDARD
KAN-23 | Phase 2 | Launch vehicle sensitivity analysis and Trade Study Matrix — KEY DELIVERABLE | WBS 2.3 — Trade-Off Analysis | 11-12 | 29 Apr 2026 | 10 May 2026 | High | Not Started | KEY DELIVERABLE
KAN-24 | Phase 3 | Document current logistics planning workflow (18-24 month lead time) | WBS 3.0 — Value Stream Mapping | 13 | 13 May 2026 | 17 May 2026 | High | Not Started | STANDARD
KAN-25 | Phase 3 | Identify and quantify waste: waiting, overproduction, defects | WBS 3.0 — Value Stream Mapping | 13 | 13 May 2026 | 17 May 2026 | High | Not Started | STANDARD
KAN-26 | Phase 3 | Design future state VSM targeting 30% cycle time reduction — MILESTONE + DELIVERABLE | WBS 3.0 — Value Stream Mapping | 14 | 20 May 2026 | 24 May 2026 | High | Not Started | MILESTONE + DELIVERABLE
KAN-27 | Phase 3 | FMEA: identify failure modes and assess severity, occurrence, detection | WBS 3.1 — FMEA | 14-15 | 20 May 2026 | 31 May 2026 | High | Not Started | STANDARD
KAN-28 | Phase 3 | Develop mitigation actions for high-RPN failure modes — KEY DELIVERABLE | WBS 3.1 — FMEA | 15 | 27 May 2026 | 31 May 2026 | High | Not Started | KEY DELIVERABLE
KAN-29 | Phase 3 | Build fault tree analysis and compile process improvement report — KEY DELIVERABLE | WBS 3.2 — Reliability | 15-16 | 27 May 2026 | 07 Jun 2026 | High | Not Started | KEY DELIVERABLE
KAN-30 | Phase 4 | Analyse international partnership dynamics: ESA, JAXA, and CSA | WBS 4.0 — Partnership Strategy | 17 | 10 Jun 2026 | 14 Jun 2026 | High | Not Started | STANDARD
KAN-31 | Phase 4 | Compare cooperative vs competitive partnership models | WBS 4.0 — Partnership Strategy | 17-18 | 10 Jun 2026 | 21 Jun 2026 | Medium | Not Started | STANDARD
KAN-32 | Phase 4 | Model ISRU integration: lunar water extraction impact on logistics | WBS 4.1 — Technology Roadmap | 18-19 | 17 Jun 2026 | 28 Jun 2026 | High | Not Started | STANDARD
KAN-33 | Phase 4 | Model Starship impact and develop three scenario analyses | WBS 4.1 — Technology Roadmap | 19 | 24 Jun 2026 | 28 Jun 2026 | High | Not Started | STANDARD
KAN-34 | Phase 4 | Assess Mars transferability and produce Technology Roadmap 2028-2040 — KEY DELIVERABLE | WBS 4.1 — Technology Roadmap | 20 | 01 Jul 2026 | 05 Jul 2026 | High | Not Started | KEY DELIVERABLE
KAN-35 | Phase 4 | Design and build Excel Decision Support Tool with MILP integration — MILESTONE + DELIVERABLE | WBS 4.2 — Decision Support Tool | 17-21 | 10 Jun 2026 | 12 Jul 2026 | High | Not Started | MILESTONE + DELIVERABLE
KAN-36 | Phase 4 | Write Dissertation Chapters 1-3: Introduction, Literature Review, Methodology | WBS 4.3 — Dissertation Writing | 17-20 | 10 Jun 2026 | 05 Jul 2026 | High | Not Started | STANDARD
KAN-37 | Phase 4 | Write Dissertation Chapters 4-6: Results, Discussion, Conclusions | WBS 4.3 — Dissertation Writing | 20-22 | 01 Jul 2026 | 19 Jul 2026 | High | Not Started | STANDARD
KAN-38 | Phase 4 | Compile Executive Summary (5-10 pages) for NASA stakeholders — KEY DELIVERABLE | WBS 4.3 — Dissertation Writing | 22 | 15 Jul 2026 | 19 Jul 2026 | High | Not Started | KEY DELIVERABLE
KAN-39 | Phase 4 | Supervisor review, proofreading, formatting, and final dissertation submission | WBS 4.4 — Finalization | 23-26 | 22 Jul 2026 | 16 Aug 2026 | High | Not Started | KEY DELIVERABLE
LEGEND: KEY DELIVERABLE — highlighted amber background in Type column ¦ LEARNING MILESTONE — highlighted steel blue in Type column ¦ MILESTONE + DELIVERABLE — both criteria apply